COMMERCIAL HANDOVER DOCUMENTATION

Operating & Maintenance
Handover Pack

Riverside House - Level 2 Office Fit-Out

| Project reference | Package | Revision | Issue date |
| --- | --- | --- | --- |
| OV-DEMO-001 | Electrical and Access Control | P01 | 28 July 2026 |

DEMONSTRATION ONLY This pack uses synthetic project names, product identifiers and records to demonstrate document-control output. It does not certify an installation, replace competent technical review, or contain real test results.

| 15 Source records | 10 Received | 3 Missing | 2 Need review |
| --- | --- | --- | --- |

Prepared by Osama Ventures

Osama Alomar | osama@osamaventures.co.uk

# Document control

| Field | Value |
| --- | --- |
| Document title | Operating & Maintenance Handover Pack |
| Project | Riverside House - Level 2 Office Fit-Out |
| Reference | OV-DEMO-001 |
| Package | Electrical and Access Control |
| Revision | P01 |
| Issue purpose | Public demonstration of document assembly and traceability only |
| Prepared by | Osama Ventures |
| Technical approval | Not provided - contractor approval required |

## Revision history

| Revision | Date | Description | Prepared by | Approval |
| --- | --- | --- | --- | --- |
| P01 | 28 July 2026 | Public synthetic demonstration issue | Osama Ventures | Not applicable |

## Contents

Handover status

Source document inventory

Missing items register

Equipment register

Drawing register

Certificate register

Warranty register

Commissioning register

Filename and revision register

Traceability and contractor approval

# 1. Handover status

ISSUE STATUS: INCOMPLETE The demonstration pack is structurally assembled, but five records remain missing or require clarification. The contractor must close the queue and approve technical content before any real project issue.

## Scope represented

The synthetic source set represents a Level 2 commercial office fit-out covering general lighting, emergency lighting, small power and access control. The document controller has organised and traced supplied evidence only.

## What this pack does not do

It does not certify, inspect or approve an installation.

It does not create missing certificates, test results, maintenance intervals or engineering decisions.

It does not treat a draft, unsigned or uncontrolled record as final.

It leaves technical acceptance with the competent contractor and client team.

# 2. Source document inventory

Every received, missing and review-state record is assigned a stable source ID. No missing file is silently removed from the register.

| ID | Document | Rev | Status | Source file | Control note |
| --- | --- | --- | --- | --- | --- |
| SRC-001 | Client handover requirements | P02 | Received | 01_Client_Requirements_P02.pdf | Defines requested handover sections and file format. |
| SRC-002 | Contractor electrical scope | C03 | Received | 02_Electrical_Scope_C03.pdf | Lists the demonstration package boundaries. |
| SRC-003 | Luminaire and emergency-light schedule | C02 | Received | 03_Luminaire_Schedule_C02.xlsx | Contains synthetic asset tags and quantities. |
| SRC-004 | Access-control equipment schedule | C01 | Received | 04_Access_Control_Schedule_C01.xlsx | Contains synthetic controller and power-supply tags. |
| SRC-005 | Lighting as-built drawing E-201 | C02 | Received | 05_E-201_Lighting_As-Built_C02.pdf | Demonstration drawing reference only. |
| SRC-006 | Small-power as-built drawing E-202 | Unknown | Missing | Not received | Listed in the client requirement but absent from the source folder. |
| SRC-007 | DEMO-LUM-01 product datasheet | 1.0 | Received | 07_DEMO-LUM-01_Datasheet.pdf | Synthetic product record created for this demonstration. |
| SRC-008 | DEMO-AC-02 product datasheet | 1.0 | Received | 08_DEMO-AC-02_Datasheet.pdf | Synthetic product record created for this demonstration. |
| SRC-009 | Electrical Installation Certificate | Final | Missing | Not received | No certificate has been supplied; no result is inferred. |
| SRC-010 | Emergency-lighting completion certificate | Final | Missing | Not received | No certificate has been supplied; no result is inferred. |
| SRC-011 | Access-control commissioning record | C01 | Received | 11_Access_Control_Commissioning_C01.pdf | Synthetic signed-status field intentionally left blank. |
| SRC-012 | Contractor warranty letter | Draft | Review | 12_Warranty_Letter_DRAFT.docx | Draft is unsigned and the commencement date is blank. |
| SRC-013 | Distribution-board circuit schedule | Unknown | Review | 13_DB-L2-01_Schedule_UNCONTROLLED.xlsx | File is marked uncontrolled and has no revision. |
| SRC-014 | Practical-completion document checklist | P01 | Received | 14_PC_Document_Checklist_P01.pdf | Used to cross-check the demonstration closeout queue. |
| SRC-015 | Access-control as-built drawing S-301 | C01 | Received | 15_S-301_Access_Control_As-Built_C01.pdf | Demonstration drawing reference only. |

# 3. Missing items register

This queue is the handover action list. Each item states why it is required, who must supply or clarify it, and the source that created the requirement.

| Item | Required record | Why flagged | Owner | Status | Source |
| --- | --- | --- | --- | --- | --- |
| MI-001 | Small-power as-built drawing E-202 | Required by SRC-001 section 4.2 and listed on SRC-014. | Installing contractor | Missing | SRC-001 p.4; SRC-014 p.1 |
| MI-002 | Electrical Installation Certificate | Named in the client handover checklist; no certificate file supplied. | Qualified electrical contractor | Missing | SRC-001 p.5; SRC-014 p.2 |
| MI-003 | Emergency-lighting completion certificate | Named in the client handover checklist; no certificate file supplied. | Qualified electrical contractor | Missing | SRC-001 p.5; SRC-014 p.2 |
| MI-004 | Signed contractor warranty with commencement date | The supplied draft has no signature or commencement date. | Installing contractor | Clarification required | SRC-012 p.1 |
| MI-005 | Controlled DB-L2-01 circuit schedule | The supplied spreadsheet is marked uncontrolled and has no revision. | Installing contractor | Clarification required | SRC-013 Sheet 1 |

# 4. Equipment register

Asset fields are transcribed from the synthetic schedules and datasheets. Blank or conflicting model data remains visible for contractor review.

| Asset ID | System | Description | Location | Qty | Make / model | Status | Source |
| --- | --- | --- | --- | --- | --- | --- | --- |
| L2-LUM-001 | General lighting | DEMO-LUM-01 linear luminaire | Level 2 open office | 24 | DemoLux / DEMO-LUM-01 | Traced | SRC-003 Sheet 1; SRC-007 p.1 |
| L2-EL-001 | Emergency lighting | Synthetic emergency bulkhead | Level 2 escape routes | 6 | Not supplied | Review | SRC-003 Sheet 1 |
| L2-AC-001 | Access control | DEMO-AC-02 two-door controller | Level 2 communications room | 1 | DemoSecure / DEMO-AC-02 | Traced | SRC-004 Sheet 1; SRC-008 p.1; SRC-011 p.1 |
| L2-PSU-001 | Access control | Synthetic access-control power supply | Level 2 communications room | 1 | Not stated | Review | SRC-004 Sheet 1 |
| DB-L2-01 | Small power | Level 2 distribution board | Level 2 electrical cupboard | 1 | Not stated | Clarification required | SRC-002 p.2; SRC-013 Sheet 1 |

# 5. Drawing register

Drawing numbers, titles, revisions and receipt states are transcribed exactly from the synthetic source set.

| Drawing | Title | Revision | Status | Source |
| --- | --- | --- | --- | --- |
| E-201 | Level 2 lighting as-built | C02 | Received | SRC-005 p.1 |
| E-202 | Level 2 small-power as-built | Unknown | Missing | SRC-001 p.4; SRC-014 p.1 |
| S-301 | Level 2 access-control as-built | C01 | Received | SRC-015 p.1 |
| DB-L2-01 | Distribution-board circuit schedule | Unknown | Review | SRC-013 Sheet 1 |

# 6. Certificate register

A certificate is recorded only when the supplied file exists. Missing or unsigned records remain clearly flagged.

| Record | Issuer | Reference | Status | Source |
| --- | --- | --- | --- | --- |
| Electrical Installation Certificate | Not supplied | Not supplied | Missing | SRC-001 p.5; SRC-014 p.2 |
| Emergency-lighting completion certificate | Not supplied | Not supplied | Missing | SRC-001 p.5; SRC-014 p.2 |
| Access-control commissioning record | Example Building Services Ltd | OV-DEMO-AC-COMM-01 | Received - signature blank | SRC-011 p.1-2 |
| Fire-alarm certificate | Outside demonstration package | Not applicable | Outside scope | SRC-002 p.1 |

# 7. Warranty register

Warranty periods and commencement dates are never inferred from product type or common practice.

| Item | Period | Commencement | Status | Source |
| --- | --- | --- | --- | --- |
| Contractor installation warranty | Not confirmed | Blank | Clarification required | SRC-012 p.1 |
| DEMO-LUM-01 manufacturer warranty | Not stated in supplied datasheet | Not stated | Missing evidence | SRC-007 p.1-2 |
| DEMO-AC-02 manufacturer warranty | Not stated in supplied datasheet | Not stated | Missing evidence | SRC-008 p.1-2 |

# 8. Commissioning register

The register reports whether a supplied record exists. It does not interpret results or declare a system commissioned.

| System | Record | Date | Status | Source |
| --- | --- | --- | --- | --- |
| Access control | Controller commissioning record | 24 July 2026 | Received - signature blank | SRC-011 p.1-2 |
| General lighting | Functional test record | Not supplied | Missing | SRC-014 p.2 |
| Emergency lighting | Completion / duration test record | Not supplied | Missing | SRC-001 p.5; SRC-014 p.2 |

# 9. Filename and revision register

Normalised names are output references only. The original source files remain untouched and traceable through their source IDs.

| Original filename | Normalised filename | Rev | Source ID | Action |
| --- | --- | --- | --- | --- |
| client reqs FINAL v2.pdf | OV-DEMO-001_01_Client-Handover-Requirements_P02.pdf | P02 | SRC-001 | Renamed in output index only |
| scope latest.pdf | OV-DEMO-001_02_Electrical-Scope_C03.pdf | C03 | SRC-002 | Renamed in output index only |
| LUM SCHEDULE_revC2.xlsx | OV-DEMO-001_03_Luminaire-Schedule_C02.xlsx | C02 | SRC-003 | Renamed in output index only |
| ac schedule.xlsx | OV-DEMO-001_04_Access-Control-Schedule_C01.xlsx | C01 | SRC-004 | Renamed in output index only |
| E201 AB.pdf | OV-DEMO-001_05_E-201-Lighting-As-Built_C02.pdf | C02 | SRC-005 | Renamed in output index only |
| demo light.pdf | OV-DEMO-001_07_DEMO-LUM-01-Datasheet_R01.pdf | R01 | SRC-007 | Renamed in output index only |
| controller data.pdf | OV-DEMO-001_08_DEMO-AC-02-Datasheet_R01.pdf | R01 | SRC-008 | Renamed in output index only |
| commissioning form.pdf | OV-DEMO-001_11_Access-Control-Commissioning_C01.pdf | C01 | SRC-011 | Renamed in output index only |
| warranty DRAFT.docx | OV-DEMO-001_12_Contractor-Warranty_DRAFT.docx | Draft | SRC-012 | Held in review queue |
| DB schedule use this.xlsx | OV-DEMO-001_13_DB-L2-01-Schedule_UNCONTROLLED.xlsx | Unknown | SRC-013 | Held in review queue |

# 10. Traceability and contractor approval

The traceability register links every material output back to a supplied source. Confidence describes transcription certainty, not technical correctness.

| Output record | Output location | Source | Confidence | Review note |
| --- | --- | --- | --- | --- |
| Project title and package | Cover / document control | SRC-001 p.1; SRC-002 p.1 | High | Contractor to approve before issue |
| L2-LUM-001 quantity and location | Equipment register | SRC-003 Sheet 1 | High | Cross-checked against SRC-005 |
| DEMO-LUM-01 model reference | Equipment register | SRC-007 p.1 | High | Synthetic product reference |
| L2-AC-001 quantity and location | Equipment register | SRC-004 Sheet 1 | High | Cross-checked against SRC-015 |
| DEMO-AC-02 model reference | Equipment register | SRC-008 p.1 | High | Synthetic product reference |
| E-202 missing status | Drawing / missing-items registers | SRC-001 p.4; SRC-014 p.1 | High | No drawing supplied |
| Electrical certificate missing status | Certificate / missing-items registers | SRC-001 p.5; SRC-014 p.2 | High | No certificate supplied |
| Warranty clarification status | Warranty / missing-items registers | SRC-012 p.1 | High | Signature and date are blank |
| DB-L2-01 revision status | Equipment / drawing registers | SRC-013 Sheet 1 | Medium | Controlled issue required |
| Access commissioning record status | Commissioning register | SRC-011 p.1-2 | High | Signature field remains blank |

## Contractor approval gate

APPROVAL REQUIRED BEFORE REAL PROJECT ISSUE The installing contractor must confirm scope, asset data, drawings, certificates, commissioning records, warranty terms and all technical statements. Osama Ventures assembles and traces supplied evidence; it does not sign technical declarations.

| Approval | Name | Role | Signature | Date |
| --- | --- | --- | --- | --- |
| Technical content approved |  |  |  |  |
| Missing-item exceptions accepted |  |  |  |  |
| Approved for client issue |  |  |  |  |